## Overview
HK Accounting System Integration & Automation
Alchemist Initiative Export — 30 April 2026
INITIATIVE DETAILS
Stage | Scoping
RAG Status | Green
Workstream | North Asia
Business Unit | HK
Priority | High
Group Owner | —
Market Owner | Vanessa Ng
Productivity Initiative Type | Revenue
Impact Type | Recurring
Planned Start Date | —
Actual Start Date | —
Planned Completion Date | 2027-03-01
Actual Completion Date | —
Actual Start Date
DESCRIPTION
End‑to‑end accounting process automation by using BC (or an alternative software) as an enabling platform and/ or additional tools to minimize manual steps across the full workflow - from client data submission and document ingestion to automated posting and final deliverables
CONTEXT & PROBLEM STATEMENT
HK Accounting teams currently operate across a mix of on‑premise tools and spreadsheets (e.g., PeachTree, Excel), with limited integration into the cloud platform (BC 360)Many core bookkeeping steps remain manual and time‑consuming (e.g., invoicing, data capture / data entry, reconciliations and preparation of end outputs), driving rework, errors and inconsistent turnaround timesThis constrains scalability and limits the ability to absorb growth without adding headcount, while also reducing standardisation and consistency across teams
MAIN ASSUMPTIONS USED IN BUSINESS CASE
25–30% productivity uplift through system integration and targeted automation Gross margin improvement driven by revenue growth with fixed cost base, enabled by productivity gains
FINANCIAL SUMMARY
Initiative Value | 1.8721
Benefit Run Rate | 18.9521
Cost Run Rate | 0.24
One-off Costs | 0.3
Benefit Run Rate
Cost Run Rate
One-off Costs

## Benefits
Benefits
Generated 30 April 2026
[5 empty] | FY26 | FY27 | FY28 | FY29 | FY30 | FY26 | [11 empty] | FY27 | [11 empty] | FY28 | [11 empty] | FY29 | [11 empty] | FY30
Name | Impact Type | Workstream | Business Unit | Service Line | FY26 | FY27 | FY28 | FY29 | FY30 | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | July | August | September | October | November | December
Actual Gross Margin | Recurring | North Asia | HK
Actual Gross Margin Uplift | Recurring | North Asia | HK
Actual Revenue Uplift | Recurring | North Asia | HK
Planned Gross Margin (base case) | Recurring | North Asia | HK |  |  | 0.31 | 0.36 | [14 empty] | 0.01 | 0.01 | 0.02 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03
Planned Gross Margin (high case) | Recurring | North Asia | HK |  |  | 0.4 | 0.48 | [14 empty] | 0.01 | 0.01 | 0.02 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04
Planned Gross Margin Uplift (base case) | Recurring | North Asia | HK |  |  | 7.35 | 8.52 | [14 empty] | 0.14 | 0.28 | 0.54 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71
Planned Gross Margin Uplift (high case) | Recurring | North Asia | HK |  |  | 8.86 | 10.32 | [14 empty] | 0.17 | 0.32 | 0.63 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86 | 0.86
Planned Revenue Uplift (base case) | Recurring | North Asia | HK |  |  | 1.0921 | 1.32 | [14 empty] | 0.022135 | 0.03 | 0.05 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11
Planned Revenue Uplift (high case) | Recurring | North Asia | HK |  |  | 1.48 | 1.8 | [14 empty] | 0.02 | 0.04 | 0.07 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15

## Costs
Costs
Generated 30 April 2026
[5 empty] | FY26 | FY27 | FY28 | FY29 | FY30 | FY26 | [11 empty] | FY27 | [11 empty] | FY28 | [11 empty] | FY29 | [11 empty] | FY30
Name | Impact Type | Workstream | Business Unit | Service Line | FY26 | FY27 | FY28 | FY29 | FY30 | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | July | August | September | October | November | December
Implementation Cost | One Off | North Asia | HK |  | 0.1 | [7 empty] | 0.1
Licensing & Operation Cost | Recurring | North Asia | HK |  |  | 0.12 | 0.12 | [14 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Vendor Consulting/Solution Cost | One Off | North Asia | HK |  | 0.2 | [9 empty] | 0.2

## Milestones
Milestones
Generated 30 April 2026
Name | Planned Start Date | Actual Start date | Planned End date | Actual End Date | Status | Responsible | Description | Checklist 1 | Checklist 2 | Checklist 3
Conduct high‑level SOP‑based assessment to quantify the opportunity size (where the manual effort sits, existing system used) | 2026-03-23 |  | 2026-04-03 |  | Completed | Zuheng Li
Develop the initial view of solution options | 2026-04-13 | 2026-04-13 | 2026-04-17 | 2026-04-17 | Completed | Venkatesh Ramakrishnaiah
Brainstorming and alignment of solution options for automation | 2026-04-20 | 2026-04-20 | 2026-04-24 | 2026-04-24 | Completed | Venkatesh Ramakrishnaiah
Effort & Investment requirement estimation | 2026-04-27 | 2026-04-27 | 2026-04-30 |  | In Progress On Track | Fikri Akbar Hedianto
Accelerate the transition of ~200 non‑BC clients by migrating them onto BC where appropriate, or onto an alternative accounting platform currently under evaluation | 2026-05-01 |  | 2026-05-31 |  | Not Started | Vanessa Ng
Project Kick-off - Lock in group & market initiative owner, establish initiative governance, develop plan & milestones, and confirm resourcing & team | 2026-04-06 |  | 2026-05-31 |  | In Progress On Track | Vanessa Ng
Conduct detailed requirements specification (functional requirements, system integration, and non‑functional requirementsincl. IT/security) | 2026-06-01 |  | 2026-07-31 |  | Not Started | Fikri Akbar Hedianto
Lock solution design (e.g. software, architecture, cloud vs on-premise, buy vs build) and overall implementation plan | 2026-08-01 |  | 2026-08-31 |  | Not Started | Fikri Akbar Hedianto
Execute phased clients migration to BC/ alternative platform | 2026-06-01 |  | 2026-10-31 |  | Not Started | Vanessa Ng
Run pilot implementation (solution build + testing) with a few selected clients | 2026-10-01 |  | 2026-11-30 |  | Not Started | Fikri Akbar Hedianto
User Acceptance Testing and Pilot Operationalization | 2026-12-01 |  | 2027-01-31 |  | Not Started | Vanessa Ng
Develop phased rollout plan post successful Pilot | 2027-02-01 |  | 2027-02-28 |  | Not Started | Vanessa Ng
Execute phased rollout (e.g., XX-YY clients/month) with structured hypercare and issue burn‑down | 2027-03-01 |  | 2027-09-30 |  | Not Started | Vanessa Ng
Set up continuous improvement cadence & automation backlog governance | 2027-01-01 |  |  |  | Not Started | Vanessa Ng

## KPIs
KPIs
Generated 30 April 2026
[10 empty] | FY26 | [11 empty] | FY27 | [11 empty] | FY28 | [11 empty] | FY29 | [11 empty] | FY30
Name | Measured | Unit | Impacted Metric | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | September | October | November | December
% of clients on BC | quarterly | #BC Clients/ Total Clients | Operational
Cycle time per process | quarterly | Hours | Operational
Gross Margin of HK Accounting Team | quarterly | Percentage (%) | Gross margin
Reduction in error rate | quarterly | #Errors | Operational
Revenue per Technical FTE | quarterly | USD (k) | Revenue

## Risks
Risks
Generated 30 April 2026
Description | Likelyhood | Impact | Risk Rating | Mitigation | Owner | Owner | Type | Status
Change adoption and capability gaps | Medium | Low |  | Mitigate via training, super‑users and post go‑live hypercare
Data migration and integration complexity (legacy formats, data quality) | High | High |  | Mitigate via mapping, cleansing, controlled pilots and parallel runs
Dependency on vendor / platform support and internal capacity | Low | High |  | Mitigate via agreed support SLAs, dedicated delivery squad and clear governance

## Status Updates
Status Updates
Generated 30 April 2026
Date | RAG | Summary | Achievements | Issues | Next Steps | Submitted By | Submitted By

## Meeting Notes
Meeting Notes
Generated 30 April 2026
Date | Notes | Actions | Actions

## _Reference (hidden)
initiative_id | cec2ffd3-25a6-43f6-b94f-67d2fc2f67c6
export_timestamp | 2026-04-30T09:47:28.655Z
version | 2
mode | single
base_fiscal_year | 2026
type | id | name
benefit | e3592a85-e137-4ba8-9575-1053082adb1e | Actual Gross Margin
benefit | 97317b9e-611a-4e27-af60-bb37dccf4ab0 | Actual Gross Margin Uplift
benefit | 98d0e876-2ca5-4f58-b1b9-92ea95a96495 | Actual Revenue Uplift
benefit | c61fa686-4626-4dca-89e7-aaa82f5f0e37 | Planned Gross Margin (base case)
benefit | 530a20c0-a3eb-48d6-9115-dcdd4c470ae5 | Planned Gross Margin (high case)
benefit | 708ab643-5017-484d-8f3b-35ac0e05f00b | Planned Gross Margin Uplift (base case)
benefit | 54bad0c0-c35b-4288-b527-647ab82dac4c | Planned Gross Margin Uplift (high case)
benefit | 398b9357-10b7-4338-8cb9-f65eb9c47aa4 | Planned Revenue Uplift (base case)
benefit | 69b703a1-415c-4f6d-8257-777a37b4de0b | Planned Revenue Uplift (high case)
cost | b3b1dd6e-0f5a-4e10-ac2c-ba2dd2e4a65a | Implementation Cost
cost | 3de083cb-583b-4cb9-9e45-14e00d031bcc | Licensing & Operation Cost
cost | f927756e-8750-45cc-9fbf-0c838d75d7df | Vendor Consulting/Solution Cost
milestone | 9d6a0f7f-f5da-4406-bc74-6671343f5fd2 | Conduct high‑level SOP‑based assessment to quantify the opportunity size (where the manual effort sits, existing system used)
milestone | f1c7fef3-75c6-4b15-bb1d-9960b3bed933 | Develop the initial view of solution options
milestone | 1dc9f7e6-074c-4b57-b3e6-8850c6d5eb4c | Brainstorming and alignment of solution options for automation
milestone | e3d6022c-c378-45ed-9bee-d57d6bcfbc9f | Effort & Investment requirement estimation
milestone | fe18df78-c14b-44e2-a46c-e7493965a8a3 | Accelerate the transition of ~200 non‑BC clients by migrating them onto BC where appropriate, or onto an alternative accounting platform currently under evaluation
milestone | 05b021f5-aed3-45c7-b30d-f35fe8ea3f95 | Project Kick-off - Lock in group & market initiative owner, establish initiative governance, develop plan & milestones, and confirm resourcing & team
milestone | 69ed5724-0636-4d0c-8051-46ec1943a30e | Conduct detailed requirements specification (functional requirements, system integration, and non‑functional requirementsincl. IT/security)
milestone | b07a50dd-2ffe-4c6f-a0d9-f71be710225e | Lock solution design (e.g. software, architecture, cloud vs on-premise, buy vs build) and overall implementation plan
milestone | 397f64e2-146e-4f65-b298-baae46903039 | Execute phased clients migration to BC/ alternative platform
milestone | 8d07aa67-8b26-4205-aa8b-cc6f3f52c2bc | Run pilot implementation (solution build + testing) with a few selected clients
milestone | 8d52731c-932a-40fb-8302-5186a4e0454e | User Acceptance Testing and Pilot Operationalization
milestone | ae91bfd6-f7de-40f6-a232-620f067af3db | Develop phased rollout plan post successful Pilot
milestone | 50b1b0a2-d93a-4763-8bf2-fe4f2cdae404 | Execute phased rollout (e.g., XX-YY clients/month) with structured hypercare and issue burn‑down
milestone | a8959d0b-8f94-45da-88d3-7d91013701c9 | Set up continuous improvement cadence & automation backlog governance
kpi | 7f7c96ba-a1f7-4151-8b06-327376107fb3 | % of clients on BC
kpi | bb43193c-8c78-4a59-8e11-561e8e2740c2 | Cycle time per process
kpi | 0b69ed07-1f58-45e4-b12c-4b12c3195242 | Gross Margin of HK Accounting Team
kpi | 0be29aea-0ab5-4214-89fa-4738aef2a9ee | Reduction in error rate
kpi | 870db982-a338-4c88-bbf1-55ea473f6327 | Revenue per Technical FTE
risk | e844f090-f260-4693-ae6f-01a38cdabde5 | Change adoption and capability gaps
risk | f716bfab-5ef0-4cef-bbbe-d8ec850b908e | Data migration and integration complexity (legacy formats, data quality)
risk | 2104546d-036a-4bb5-b0c9-e74f70732d70 | Dependency on vendor / platform support and internal capacity